## How to use
How to use this template
1 | A short one paragraph summary, so the project can be quickly understood by others using this plan. | Project Page
2 | Develop the stakeholder register from the early stages of the project. This will help you keep tabs on who you have engaged with, their view of the project and contact details in one place. You may choose to keep note of recent contact or attendance at engagement events. Remember this is a live document. The information you include about stakeholders at this stage, may evolve and change. Over time, generic stakeolder groups may become more nuanced. (E.g. a whole school may be "keep informed" but a student steering group may be highly involved and participate in some decision-making.) | Stakeholder register
3 | You may wish to use the stakeholder mapping tools to scope out potential stakeholders and level of interest and influence. This is a helpful exercise to involve the wider project team to get holistic understanding of stakeholders and gaps in knowledge. There are two approaches to mapping out stakeholders that may be helpful as an exercise in thinking about them and there needs. The first may be more familiar; mapping out interest and influence. The second encouages you to map stakeholders in a visual way based on their possible attitudes to the project and likely influence. This may be a useful workshopping tool in thinking about how to approach your engagement. | Stakeholder mapping tools
4 | Use this to plan engagement activities. Draw through stakeholders from your register and consider how each may be included, either separately or together with other individuals and groups. Although you may identify some stakeholders as low influence, it may add valuable insghts to the project as well as contribute to your social value to consider how, through your approach to engagment they could be enabled to have greater influence. | Engagement plan
5 | Through any engagement activity you carry out, new stakeholders may come to light. Add them to your register. | Engagement report
6 | This list of stakeholder groups can provide a helpful prompt of what types of organisation or category of stakeholder is helpful to consider. Cross reference with your own list to identify stakeholders you may have overlooked. | Stakeholder groups

## Project Page
Project Name
Project Reference
Project Summary
Responsible Person/ People

## Stakeholder Register
Stakeholder Register Comply with GDPR and ensure this can be accessed as needed. Remember that during construction for example the construction lead might need to access this information together with the engagement lead to plan effective engagement during the this phase.
Stakeholder | Type | Relationship with project | Contact Person | Details (Phone, Email, Website, Address) | Interest (How much does the project interest them?) | Influence (How much influence do they have over the project?) | How will you interact with the stakeholder? | How do they feel towards the project | Notes / Comments | Most recent engagement / contact
EG Yoga Café | Commercial | Involved | Jo Miller - Director | Jo.Miller@YogaCafe.org.uk | High | Medium | Engage (Manage closely) | Negative | Concerned around parking and impact on business
High
Medium

## Stakeholder Map
By mapping out stakeholders by attitude to project, you can start to consider where your priorities should be in engagement, what the key concerns are and how you can addres them.
By mapping out stakeholders by attitude to project, you can start to consider where your priorities should be in engagement, what the key concerns are and how you can addres them.
Stakeholder Map:
You may wish to use this map as an option to visually represent the stakeholders involved in your project. It's a useful format for workshopping and mapping out your stakeholders with a project team and steering group. Below are two approaches to thinking about your stakeholders, their relationship to the project and to each other.
Consider where you have the opportunity to increase influence, especially amoung under-represented groups and those who have been historically left out of planning decision making processes. The below is an example. You can use other tools (e.g. online whiteboards such as Miro, JamBoard, simple word documents or post-its).
Influence
Interest
High influence, less interested: Consult (Keep satisfied)
High influence, highly interested: Engage (manage closely)
Low influence, less interested: Monitor
Low influence, highly interested: Keep informed (involve adequately)
Yoga Cafe
Collie Primary
Brenda Bicycle MSP
Level of power / influence
Attitude to project
Highly positive
Neutral
Highly negative
Low
High

## Engagement plan
Engagement Plan
Fill in the boxes below (write over the prompts)
Engagement Lead | Who is responsible?
Project background | What is the proposed project, what, where, who for, purpose
Engagement context | Engagement context - what engagement has already taken place. This helps to understand what is already known, to be mindful of what engagement and consultation communities have recently participated in and what learning there is, either from the outcomes or the way in which engagement took place.
Community / Locality context | Nature of community / communities impacted by this project
Project stage
Engagement Objectives | Overarching reasons for engagement for this stage - what does the project team need to get out of this engagement? (specifics may be different at different events - include that in the plan below, here provide overarching objectives)
Limitations | What cannot change at this stage? What is fixed and are there any red lines? (this is about managing expectations and knowling what can and cannot be asked in engagement)
Activity plan
Stakeholder group | Purpose | Activity | When / frequency | Promotion of engagement | Responsible person / lead | Resources / costs | Status | Notes
Which stakeholders targeted. As specific as possible, eg Cupar Toddler group, rather than "community". | Why do you want to engage with them, what input are you expecting them to provide? | What type of activity will you do to engage with them, e.g. focus group and comment cards? | When and how often? List dates and times if they are known/planned. | How do you intend to invite and communicate with this audience to partake in the community engagement activities? Specify media chosen and frequency. Link to comms plan. | Who is leading on this activity and who else is involved? Include contact details. | Detail what is needed alongisde people for the event. | Planned / Active / Complete / Postponed / Cancelled | Other relevant information.
E.g., P1-4 pupils at Xy School | Gain insight on how they like to travel to school and what barriers they face. | Classroom based map exercise and site walk. (see separate session plan) | Twice during stage 0-1. 02/03/24 and 14/09/24. | Via the class teacher and letter home to parents. | J. Smith, project lead, 07123 456 789 | £50 for maps and pens. | Planned | Teacher is very keen and cycles to school herself.
This template provides a useful structure when planning community engagement activities. This format can be updated to reflect changing activities at different RIBA stages and may provide additional support whilst compiling a Communications Plan and report at each stage review.
Each engagement activity may require a more detailed execution plan as well the the list of activities below.
For additional guidance please refer to the Community Engagement Guide which sets out:
> guidance for effective engagement for active travel infrastructure projects
> examples of good practice
> resources for planning engagement activity
> signposting to resources and organisations to improve quality and effectiveness of engagement
> understanding of what support Sustrans can provide.

## Engagement report
Engagement Report
Engagement activity | Purpose | When? | Attendees | Data / findings | Outcomes | Risks identified | Opportunities identified | Next steps | Notes
| What was the purpose of engagement? |  | Numbers and demographic information | Include data, quotes and evidence gathered from engagement. | What was learnt from the engagement? | As a result of the engagement have any new risks to the project success been identified? |  | What will happen with the information gathered? How will you feed this information back to the communities that gave it? AND what are the next steps in engagement? | Other relevant information including learning from event.

## Stakeholder groups - examples
Age based groups (youth groups etc.)
Businesses (e.g. individual businesses, Chamber of Commerce)
Care services
Community, special interest and resident groups
Community Councils
Community Development Trusts
Elected representatives (Councillors, MSPs)
Education facilities and users – e.g. schools (e.g. staff, students, parents etc.)
Environmental groups
Emergency services
Faith groups
Leisure facilities
Local authorities and relevant departments e.g. Community Planning Partnership
Local charities and the voluntary sector
Media (Newspapers, TV)
National charities with a local branch/presence
Neighbourhood leaders
People traveling through the community e.g. rail passengers
Property owners
Property tenants and leaseholders
Residents (break into subsets as required e.g. car owner, age, employment status etc).
Support groups
Sports groups
Tourists and visitors
Third Sector Interface organisations (TSI) or Voluntary Action Groups
Utility providers e.g. water, electricity, waste
Workplaces & employers
List of potential stakeholder groups
Below is a guide to some of the generic stakeholder groups that you may consider for your stakeholder mapping.
The most basic pre-engagement research should identify the individuals, organisations and groups which comprise and represent the community.
This will help you to understand the community and also inform your engagement plan.
Effective engagement must reach a broad spectrum of the stakeholders, not just members who are the most prominent or vocal.
Remember your stakeholder map should be specific to your project context. For example, it is not sufficient for a Places for Everyone project to identify “businesses” or “schools” as stakeholders. We would expect a list of business names or school names that you have mapped and sought to understand in terms of interest in the project etc.
General stakeholder list includes, but is not limited to

## Drop Downs
Type (macro level) | Categories | Interest (How much does the project interst them?) | Influence (How much influence do they have over the project?) | How will you interact with stakeholder | How do they feel towards the project
Commercial | Influencer | Low | Low | Consult (Keep satisfied) | Positive
Residential | Affected | Medium | Medium | Engage (Manage closely) | Neutral
Educational | Involved | High | High | Keep informed (involve adquately) | Negative
Political | Other |  |  | Monitor
Leisure
Services
Other
N.B.
You can update and amend the drop downs to suit your needs.
The drop downs have been created using the data validation tool (validation criteria: list). Go to the tab Data and select Data Validation.
Stakeholder categories | Stakeholders fall into three categories
Inluencer | Those who can influence the project
Affected | Those who are affected by the project
Involved | Those who are involved in the project
Other